## Общие сведения
Гуманитарная заявка
Наименование госоргана (организации)
УНП госоргана (организации)
Название проекта | Мечтай - иди - живи!
Продолжительность проекта, лет | 1
Организация-заявитель, предлагающая проект
УНП | 590771263
Название | Государственное учреждение "Территориальный центр социального обслуживания населения Волковысского района" (далее - ТЦСОН Волоквысского района)
Адрес | Республика Беларусь, Гродненская область, город Волковыск, ул. Победы, 4
Должность ответственного лица | Заведующий отделением социальной реабилитации, абилитации инвалидов
ФИО ответственного лица | Варчак Наталья Владимировна
Контактные данные для связи | 801512 61733, volkovysk.r-tc@mintrud.by
Целевая группа | Инвалиды, подопечные отделения социальной реабилитации, абилитации инвалидов ТЦСОН Волоквысского района, в количестве 30 человек в возрасте 20-40 лет.
Место реализации проекта | Волковысский район и город Волковыск
Обоснование проблемы с учетом исходной ситуации в регионе реализации проекта | По состоянию на 1 февраля 2025 года отделение социальной реабилитации, абилитации инвалидов посещают 66 инвалидов, из них 32 – I группы, 34 – II группы, 9 инвалидов-колясочников, 4 инвалида по зрению и 1 инвалид по слуху. Одним из важных способов в практике реабилитации инвалидов становится туризм, который не только способствует физической реабилитации, но и играет важную роль в социальном и эмоциональном восстановлении инвалидов, помогая им вести полноценную и активную жизнь. Изменение обстановки, новые впечатления и возможность общения с другими людьми снижают уровень стресса и депрессии. Пребывание на свежем воздухе, умеренные физические нагрузки и другие факторы туризма способствуют укреплению мышц, улучшению координации, целом укреплению здоровья. Туризм способствует взаимодействию инвалидов с окружающим миром, что помогает преодолеть чувство изоляции. К сожалению, в сегодняшних реалиях некоторые инвалиды пока еще ограничены в возможностях получения новых впечатлений. Круг их жизни зачастую замкнут – дом, отделение, дом... И то, что для обычного человека легко и доступно – купить путевку, сесть в машину или на самолет, отправиться в туристический поход, для инвалидов является часто недостижимым. Учитывая стремление инвалидов нашего отделения к активной и полноценной жизни, необходимо позаботиться о создании для них всех условий для комфортного, безопасного и интересного отдыха, что мы и постараемся создать за счет проекта.
Цель проекта | Социальная реабилитация и адаптация людей с инвалидностью путем организации социального туризма.
Краткое содержание (суть) проекта | Основные разделы проекта: 1. Экологического туризма. 2. Культурно-просветительского туризма. 3. Виртуального туризма. 4. Туризма с целью отдыха. В экологическое направление войдет посещение мест не тронутой человеком природой; посещение родников, памятников природы, посещение парков, скверов. В культурно-просветительский туризм вид социального туризма, который охватывает собой посещение исторических, культурных и географических достопримечательностей нашего района, Гродненской области, Республики Беларусь. Виртуальный туризм даст возможность инвалидам, благодаря современным и техническим технологиям познакомиться с шедеврами Белорусской культуры, а также посетить достопримечательности Республики Беларусь и Российской Федерации (города-побратимы Гусев и Бирск), позволяя виртуально путешествовать. Туризм с целью отдыха включит в себя поездки на рыбалку, за грибами, пикники, соревнования на природе, посиделки.
Финансирование проекта
Количество поступлений (план) | 1
Валюта | EUR
Общая стоимость проекта | 5000
Средства донора | 4520
Софинансирование | 480
Дальнейшая деятельность по окончании проекта | 1. Продолжится познавательная, туристическая деятельность инвалидов. 2. Будут организованы туристические мероприятия с участием свыше пятидесяти людей с инвалидностью. 3. По основам виртуального туризма будут организованы и проведены занятия через интернет для людей с инвалидностью с тяжелыми, множественными нарушениями в рамках кружка на дому.

## Задачи проекта
Задачи, планируемые к выполнению в рамках реализации проекта:
Развивать познавательный и активный досуг инвалидов путем организации социального туризма.
Дать возможность людям с инвалидностью получить новые эмоции и впечатления, посещая культурные достопримечательности.
Расширять границы информационного и досугового пространства, стимулировать интерес к краеведению, изучению истории родного края
Укрепить и сохранить здоровье, закалить организм, повысить работоспособность и двигательную активность.

## Мероприятия
Краткое описание мероприятий в рамках проекта:
Круглый стол по запуску проекта
разработка информационных буклетов
презентации туристических маршрутов Республики Беларусь
уроки-практикумы
туристические поездки по Республике Беларусь
велоэкскурсии
экскурсии
виртуальные туры по достопримечательностям городов-побратимов Российской Федерации
пешие прогулки
промышленные туристические туры по предприятиям Республики Беларусь
создание фоточелленджей
создание раздела по реализации проекта на сайте ТЦСОН Волковысского района
съемка видеосюжетов и видеофильма
запись интервью с представителями целевой группы

## Ожидаемые результаты
Ожидаемые результаты:
Продолжится познавательная, туристическая деятельность инвалидов
будут организованы туристические мероприятия с участием свыше пятидесяти людей с инвалидностью
по основам виртуального туризма будут организованы и проведены занятия через интернет для людей с инвалидностью с тяжелыми, множественными нарушениями в рамках кружка на дому

## Агрегация данных
Заявка на гуманитарный проект
Организация-заявитель, предлагающая проект | Государственное учреждение "Территориальный центр социального обслуживания населения Волковысского района" (далее - ТЦСОН Волоквысского района)
УНП | 590771263
Адрес | Республика Беларусь, Гродненская область, город Волковыск, ул. Победы, 4
Должность ответственного лица | Заведующий отделением социальной реабилитации, абилитации инвалидов
ФИО ответственного лица | Варчак Наталья Владимировна
Контактные данные для связи | 801512 61733, volkovysk.r-tc@mintrud.by
Название проекта | Мечтай - иди - живи!
Продолжительность проекта, лет | 1
Целевая группа | Люди с инвалидностью, подопечные отделения социальной реабилитации, абилитации инвалидов ТЦСОН Волоквысского района, в количестве 30 человек в возрасте 20-40 лет.
Место реализации проекта | Волковысский район и город Волковыск
Обоснование проблемы с учетом исходной ситуации в регионе реализации проекта | По состоянию на 1 февраля 2025 года отделение социальной реабилитации, абилитации инвалидов посещают 66 инвалидов, из них 32 – I группы, 34 – II группы, 9 инвалидов-колясочников, 4 инвалида по зрению и 1 инвалид по слуху. Одним из важных способов в практике реабилитации инвалидов становится туризм, который не только способствует физической реабилитации, но и играет важную роль в социальном и эмоциональном восстановлении инвалидов, помогая им вести полноценную и активную жизнь. Изменение обстановки, новые впечатления и возможность общения с другими людьми снижают уровень стресса и депрессии. Пребывание на свежем воздухе, умеренные физические нагрузки и другие факторы туризма способствуют укреплению мышц, улучшению координации, целом укреплению здоровья. Туризм способствует взаимодействию инвалидов с окружающим миром, что помогает преодолеть чувство изоляции. К сожалению, в сегодняшних реалиях некоторые инвалиды пока еще ограничены в возможностях получения новых впечатлений. Круг их жизни зачастую замкнут – дом, отделение, дом... И то, что для обычного человека легко и доступно – купить путевку, сесть в машину или на самолет, отправиться в туристический поход, для инвалидов является часто недостижимым. Учитывая стремление инвалидов нашего отделения к активной и полноценной жизни, необходимо позаботиться о создании для них всех условий для комфортного, безопасного и интересного отдыха, что мы и постараемся создать за счет проекта.
Цель проекта | Социальная реабилитация и адаптация людей с инвалидностью путем организации социального туризма. | Социальная реабилитация и адаптация людей с инвалидностью путем организации социального туризма.
Краткое содержание (суть) проекта | Основные разделы проекта: 1. Экологического туризма. 2. Культурно-просветительского туризма. 3. Виртуального туризма. 4. Туризма с целью отдыха. В экологическое направление войдет посещение мест не тронутой человеком природой; посещение родников, памятников природы, посещение парков, скверов. В культурно-просветительский туризм вид социального туризма, который охватывает собой посещение исторических, культурных и географических достопримечательностей нашего района, Гродненской области, Республики Беларусь. Виртуальный туризм даст возможность инвалидам, благодаря современным и техническим технологиям познакомиться с шедеврами Белорусской культуры, а также посетить достопримечательности Республики Беларусь и Российской Федерации (города-побратимы Гусев и Бирск), позволяя виртуально путешествовать. Туризм с целью отдыха включит в себя поездки на рыбалку, за грибами, пикники, соревнования на природе, посиделки.
Количество поступлений (план) | 1
Валюта | EUR
Общая стоимость проекта | 5000
Средства донора | 4520
Софинансирование | 480
Дальнейшая деятельность по окончании проекта | 1. Продолжится познавательная, туристическая деятельность инвалидов. 2. Будут организованы туристические мероприятия с участием свыше пятидесяти людей с инвалидностью. 3. По основам виртуального туризма будут организованы и проведены занятия через интернет для людей с инвалидностью с тяжелыми, множественными нарушениями в рамках кружка на дому.
Задачи, планируемые к выполнению в рамках реализации проекта | Развивать познавательный и активный досуг инвалидов путем организации социального туризма. Дать возможность людям с инвалидностью получить новые эмоции и впечатления, посещая культурные достопримечательности. Расширять границы досугового и информационного пространства, стимулировать интерес к краеведению, изучению истории своего края. Укрепить и сохранить здоровье, закалить организм, повысить работоспособность и двигательную активность
Краткое описание мероприятий в рамках проекта | Основные разделы проекта: 1. Экологического туризма. 2. Культурно-просветительского туризма. 3. Виртуального туризма. 4. Туризма с целью отдыха. В экологическое направление войдет посещение мест не тронутой человеком природой; посещение родников, памятников природы, посещение парков, скверов. В культурно-просветительский туризм вид социального туризма, который охватывает собой посещение исторических, культурных и географических достопримечательностей нашего района, Гродненской области, Республики Беларусь. Виртуальный туризм даст возможность инвалидам, благодаря современным и техническим технологиям познакомиться с шедеврами Белорусской культуры, а также посетить достопримечательности Республики Беларусь и Российской Федерации (города-побратимы Гусев и Бирск), позволяя виртуально путешествовать. Туризм с целью отдыха включит в себя поездки на рыбалку, за грибами, пикники, соревнования на природе, посиделки.
Ожидаемые результаты | Продолжится познавательная, туристическая деятельность инвалидов. Будут организованы туристические мероприятия с участием свыше пятидесяти людей с инвалидностью. По основам виртуального туризма будут организованы и проведены занятия через интернет для людей с инвалидностью с тяжелыми, множественными нарушениями в рамках кружка на дому
Развивать познавательный и активный досуг инвалидов путем организации социального туризма.
Развивать познавательный и активный досуг инвалидов путем организации социального туризма.
Обновить

## Overview
Humanitarian project application
The project title | Dream - go - live!
The Project duration, years | 1
Applicant organisation proposing the project
Organisation name | State Institution «Territorial Center for Social Services for the Population of Volkovysk District»
Address | Republic of Belarus, Grodno region, Volkovysk, st. Pobeda, 4
Position of the contact person | Head of the department of social rehabilitation, habilitation of disabled people
Name, surname of the contact person | Varchak Natalya Vladimirovna
Contact details for liaison | 801512 61733, volkovysk.r-tc@mintrud.by
The Target group | Рeople with disabilities, wards of the department of social rehabilitation, habilitation of disabled people of the state institution «Territorial Center for Social Services for the Population of the Volkovysk District», in the amount of 30 people aged 20-40 years.
Place of project realisation | Volkovysk district, Volkovysk
Justification of the problem taking into account the baseline situation in the project region | As of February 1, 2025, the department of social rehabilitation and habilitation of disabled people is attended by 66 disabled people, of which 32 are group I, 34 are group II, 9 wheelchair users, 4 visually impaired and 1 hearing impaired. Tourism is becoming one of the important ways in the practice of rehabilitation of people with disabilities, which not only promotes physical rehabilitation, but also plays an important role in the social and emotional recovery of people with disabilities, helping them lead a more fulfilling and active life. Changing the environment, new experiences, and the opportunity to communicate with other people reduce stress and depression levels. Outdoor activities, moderate physical activity, and other tourism factors promote health, strengthen muscles, and improve coordination. Tourism promotes the interaction of people with disabilities with the outside world, which helps to overcome feelings of isolation. Unfortunately, in today's realities, some people with disabilities are still limited in their opportunities to gain new experiences. Their circle of life is often closed – home, office, home... And what is easy and affordable for an ordinary person – to buy a ticket, get in a car or plane, go on a camping trip, is often unattainable for people with disabilities. Considering the desire of our people with disabilities for an active and fulfilling life, it is necessary to take care of creating for them all the conditions for a comfortable, safe and interesting holiday, which we will try to create through the project.
Project Aim | Social rehabilitation and adaptation of people with disabilities through the organization of social tourism.
Project Summary | Main sections of the project: 1. Eco-tourism. 2. Cultural and educational tourism. 3. Virtual tourism. 4. Tourism for recreational purposes. The environmental direction will include visiting places untouched by nature; visiting springs, natural monuments, visiting parks, squares. Cultural and educational tourism is a type of social tourism that includes visiting historical, cultural and geographical attractions of our region, Grodno region, and the Republic of Belarus. Virtual tourism will give people with disabilities the opportunity, thanks to modern and technical technologies, to get acquainted with the masterpieces of Belarusian culture, as well as visit the sights of the Republic of Belarus and the Russian Federation (sister cities Gusev and Birsk), allowing them to travel virtually. Tourism for the purpose of recreation will include fishing trips, mushroom picking, picnics, outdoor competitions, and get-togethers.
Total project funding
Planned number of trenches | 1
Currency | EUR
Total | 5000
Donor funds | 4520
Co-financing | 480
Further activities at the end of the project | 1. Educational and tourism activities of disabled people will continue. 2. Tourist activities will be organized with the participation of over fifty people with disabilities. 3. On the basics of virtual tourism, classes will be organized and conducted via the Internet for people with disabilities with severe, multiple impairments as part of a home study group. 4. Attracting public attention to the implementation of the project and the development of social tourism among people with disabilities through the publication of articles in the regional newspaper «Nash Chas», the republican newspaper «Vmeste», as well as on the Internet on the website of the state institution «Territorial Center for Social Services for the Population of the Volkovysk District».

## Project Objectives
The envisaged objectives during the project work:
To develop educational and active leisure for people with disabilities by organizing social tourism.
To give people with disabilities the opportunity to experience new emotions and impressions by visiting cultural attractions.
To expand the boundaries of information and leisure space, to stimulate interest in local history, and to study the history of the native land
Strengthen and maintain health, strengthen the body, increase efficiency and physical activity

## Project Activities
Description of project activities:
Round table on the launch of the project
development of information booklets
presentations of tourist routes of the Republic of Belarus
workshops
tourist trips around the Republic of Belarus
bike tours
excursions
virtual tours of attractions
sister cities of the Russian Federation
hiking
industrial tourist tours
by enterprises of the Republic of Belarus
creating photo challenges
creation of a section on project implementation

## Expected Result
Expected Result:
Educational and tourism activities of disabled people will continue
tourist activities will be organized with the participation of over fifty people with disabilities
on the basics of virtual tourism, classes will be organized and conducted via the Internet for people with disabilities with severe, multiple impairments as part of a home study group

## Data aggregation
Humanitarian project application
Organisation name | State Institution «Territorial Center for Social Services for the Population of Volkovysk District»
Address | Republic of Belarus, Grodno region, Volkovysk, st. Pobeda, 4
Position of the contact person | Head of the department of social rehabilitation, habilitation of disabled people
Name, surname of the contact person | Varchak Natalya Vladimirovna
Contact details for liaison | 801512 61733, volkovysk.r-tc@mintrud.by
The project title | Dream - go - live!
The Project duration, years | 1
The Target group | Рeople with disabilities, wards of the department of social rehabilitation, habilitation of disabled people of the state institution «Territorial Center for Social Services for the Population of the Volkovysk District», in the amount of 30 people aged 20-40 years.
Place of project realisation | Volkovysk district, Volkovysk
Justification of the problem taking into account the baseline situation in the project region | As of February 1, 2025, the department of social rehabilitation and habilitation of disabled people is attended by 66 disabled people, of which 32 are group I, 34 are group II, 9 wheelchair users, 4 visually impaired and 1 hearing impaired. Tourism is becoming one of the important ways in the practice of rehabilitation of people with disabilities, which not only promotes physical rehabilitation, but also plays an important role in the social and emotional recovery of people with disabilities, helping them lead a more fulfilling and active life. Changing the environment, new experiences, and the opportunity to communicate with other people reduce stress and depression levels. Outdoor activities, moderate physical activity, and other tourism factors promote health, strengthen muscles, and improve coordination. Tourism promotes the interaction of people with disabilities with the outside world, which helps to overcome feelings of isolation. Unfortunately, in today's realities, some people with disabilities are still limited in their opportunities to gain new experiences. Their circle of life is often closed – home, office, home... And what is easy and affordable for an ordinary person – to buy a ticket, get in a car or plane, go on a camping trip, is often unattainable for people with disabilities. Considering the desire of our people with disabilities for an active and fulfilling life, it is necessary to take care of creating for them all the conditions for a comfortable, safe and interesting holiday, which we will try to create through the project.
Project Aim | Social rehabilitation and adaptation of people with disabilities through the organization of social tourism.
Project Summary | Main sections of the project: 1. Eco-tourism. 2. Cultural and educational tourism. 3. Virtual tourism. 4. Tourism for recreational purposes. The environmental direction will include visiting places untouched by nature; visiting springs, natural monuments, visiting parks, squares. Cultural and educational tourism is a type of social tourism that includes visiting historical, cultural and geographical attractions of our region, Grodno region, and the Republic of Belarus. Virtual tourism will give people with disabilities the opportunity, thanks to modern and technical technologies, to get acquainted with the masterpieces of Belarusian culture, as well as visit the sights of the Republic of Belarus and the Russian Federation (sister cities Gusev and Birsk), allowing them to travel virtually. Tourism for the purpose of recreation will include fishing trips, mushroom picking, picnics, outdoor competitions, and get-togethers.
Planned number of trenches | 1
Currency | EUR
Total | 5000
Donor funds | 4520
Co-financing | 480
Further activities at the end of the project | Educational and tourism activities of disabled people will continue, tourist activities will be organized with the participation of over fifty people with disabilities, on the basics of virtual tourism, classes will be organized and conducted via the Internet for people with disabilities with severe, multiple impairments as part of a home study group
The envisaged objectives during the project work | To develop educational and active leisure for people with disabilities by organizing social tourism. To give people with disabilities the opportunity to experience new emotions and impressions by visiting cultural attractions. To expand the boundaries of information and leisure space, to stimulate interest in local history, and to study the history of the native land Strengthen and maintain health, strengthen the body, increase efficiency and physical activity
Description of project activities | Round table on the launch of the project; development of information booklets; presentations of tourist routes of the Republic of Belarus; workshops; tourist trips around the Republic of Belarus; bike tours; excursions; virtual tours of attractions; sister cities of the Russian Federation; hiking; industrial tourist tours; by enterprises of the Republic of Belarus; creating photo challenges; creation of a section on project implementation
Expected Result | Educational and tourism activities of disabled people will continue; tourist activities will be organized with the participation of over fifty people with disabilities; on the basics of virtual tourism, classes will be organized and conducted via the Internet for people with disabilities with severe, multiple impairments as part of a home study group
Обновить

## Справочник
Справочник валют
USD | Доллар США
EUR | Евро
GBP | Фунт стерлингов
CHF | Швейцарский франк
CNY | Китайский юань
BYN | Белорусский рубль
RUB | Российский рубль