## Общие сведения
Гуманитарная заявка
Наименование госоргана (организации)
УНП госоргана (организации)
Название проекта | «Радужный дворик»
Продолжительность проекта, лет | 1
Организация-заявитель, предлагающая проект
УНП | 500031788
Название | Государственное учреждение «Василишковский детский социальный пансионат «Васильки»
Адрес | Гродненская обл .Щучинский р-н аг.Головичполье ул.Юбилейная, 2
Должность ответственного лица | Воспитатель
ФИО ответственного лица | Петуховская Светлана Николаевна
Контактные данные для связи | 375336552576
Целевая группа | Дети-инвалиды с особенностями психофизического развития
Место реализации проекта | Гродненская обл .Щучинский р-н аг.Головичполье ул.Юбилейная, 2
Обоснование проблемы с учетом исходной ситуации в регионе реализации проекта | В регионе отсутствует специализированная безопасная и адаптированная игровая площадка для детей с ограниченными возможностями психофизического развития; недостаток таких условий снижает возможности укрепления здоровья, развития физических, когнитивных и творческих навыков детей
Цель проекта | Создание безопасной и доступной среды для физического, психического и эмоционального развития детей-инвалидов с особенностями психофизического развития.
Краткое содержание (суть) проекта | Проект предполагает организацию летней оздоровительной площадки, где будут проводиться различные мероприятия, направленные на укрепление здоровья, развитие интересов и способностей детей-инвалидов с особенностями психофизического развития. В рамках проекта дети будут участвовать в спортивных мероприятиях, творческих занятиях и других развлекательных и познавательных мероприятиях. Особое внимание будет уделено формированию у детей навыков здорового образа жизни, самообслуживания, культуры поведения.
Финансирование проекта
Количество поступлений (план) | 1
Валюта | BYN
Общая стоимость проекта | 25000
Средства донора | 25000
Софинансирование | 0
Дальнейшая деятельность по окончании проекта | После завершения проекта площадка будет использоваться как постоянный ресурс для оздоровительных и развивающих занятий детей пансионата в летний период. Планируется регулярное проведение спортивных, творческих и развивающих мероприятий, а также вовлечение новых воспитанников. Опыт организации и эксплуатации площадки будет использоваться для планирования аналогичных проектов и распространения методик работы с детьми с ограниченными возможностями развития в других учреждениях региона.

## Задачи проекта
Задачи, планируемые к выполнению в рамках реализации проекта:
создать условия для безопасной и доступной игровой среды, адаптированной к потребностям детей детей-инвалидов с особенностями психофизического развития; развивать творческий потенциал, укреплять физическое, психическое и эмоциональное здоровье
предоставить возможность для активного отдыха и физической активности на свежем воздухе
организовать разнообразные и интересные игровые мероприятия, способствующие развитию различных навыков и умений; создать благоприятную атмосферу для развития дружеских отношений между детьми
содействовать развитию у детей навыков самообслуживания, самостоятельности и ответственности

## Мероприятия
Краткое описание мероприятий в рамках проекта:
Проведение спортивных занятий: эстафеты, игры на свежем воздухе, адаптированные упражнения
творческие мастер-классы: рисование, лепка, поделки, музыкальные занятия
развивающие игры и занятия для формирования когнитивных и коммуникативных навыков
обучение навыкам здорового образа жизни: гигиена, правильное питание, культура поведения; экскурсии и прогулки на площадке с использованием адаптированных элементов
игровая деятельность на безопасных адаптированных горках, качелях, каруселях и песочницах

## Ожидаемые результаты
Ожидаемые результаты:
Повышение физической активности и укрепление здоровья детей с особенностями психофизического развития
развитие творческих, когнитивных и коммуникативных навыков
формирование навыков здорового образа жизни и культуры поведения
вовлечённость детей в полезную и безопасную игровую и образовательную деятельность
создание доступной и безопасной среды для оздоровления и социализации воспитанников

## Агрегация данных
Заявка на гуманитарный проект
Организация-заявитель, предлагающая проект | Государственное учреждение «Василишковский детский социальный пансионат «Васильки»
УНП | 500031788
Адрес | Гродненская обл .Щучинский р-н аг.Головичполье ул.Юбилейная, 2
Должность ответственного лица | Воспитатель
ФИО ответственного лица | Петуховская Светлана Николаевна
Контактные данные для связи | 375336552576
Название проекта | «Радужный дворик»
Продолжительность проекта, лет | 1
Целевая группа | Дети-инвалиды с особенностями психофизического развития
Место реализации проекта | Гродненская обл .Щучинский р-н аг.Головичполье ул.Юбилейная, 2
Обоснование проблемы с учетом исходной ситуации в регионе реализации проекта | В регионе отсутствует специализированная безопасная и адаптированная игровая площадка для детей с ограниченными возможностями психофизического развития; недостаток таких условий снижает возможности укрепления здоровья, развития физических, когнитивных и творческих навыков детей
Цель проекта | Создание безопасной и доступной среды для физического, психического и эмоционального развития детей-инвалидов с особенностями психофизического развития.
Краткое содержание (суть) проекта | Проект предполагает организацию летней оздоровительной площадки, где будут проводиться различные мероприятия, направленные на укрепление здоровья, развитие интересов и способностей детей-инвалидов с особенностями психофизического развития. В рамках проекта дети будут участвовать в спортивных мероприятиях, творческих занятиях и других развлекательных и познавательных мероприятиях. Особое внимание будет уделено формированию у детей навыков здорового образа жизни, самообслуживания, культуры поведения.
Количество поступлений (план) | 1
Валюта | BYN
Общая стоимость проекта | 25000
Средства донора | 25000
Софинансирование | 0
Дальнейшая деятельность по окончании проекта | После завершения проекта площадка будет использоваться как постоянный ресурс для оздоровительных и развивающих занятий детей пансионата в летний период. Планируется регулярное проведение спортивных, творческих и развивающих мероприятий, а также вовлечение новых воспитанников. Опыт организации и эксплуатации площадки будет использоваться для планирования аналогичных проектов и распространения методик работы с детьми с ограниченными возможностями развития в других учреждениях региона.
Задачи, планируемые к выполнению в рамках реализации проекта | создать условия для безопасной и доступной игровой среды, адаптированной к потребностям детей детей-инвалидов с особенностями психофизического развития; развивать творческий потенциал, укреплять физическое, психическое и эмоциональное здоровье; предоставить возможность для активного отдыха и физической активности на свежем воздухе; организовать разнообразные и интересные игровые мероприятия, способствующие развитию различных навыков и умений; создать благоприятную атмосферу для развития дружеских отношений между детьми; содействовать развитию у детей навыков самообслуживания, самостоятельности и ответственности
Краткое описание мероприятий в рамках проекта | Проведение спортивных занятий: эстафеты, игры на свежем воздухе, адаптированные упражнения; творческие мастер-классы: рисование, лепка, поделки, музыкальные занятия; развивающие игры и занятия для формирования когнитивных и коммуникативных навыков; обучение навыкам здорового образа жизни: гигиена, правильное питание, культура поведения; экскурсии и прогулки на площадке с использованием адаптированных элементов; игровая деятельность на безопасных адаптированных горках, качелях, каруселях и песочницах
Ожидаемые результаты | Повышение физической активности и укрепление здоровья детей с особенностями психофизического развития; развитие творческих, когнитивных и коммуникативных навыков; формирование навыков здорового образа жизни и культуры поведения; вовлечённость детей в полезную и безопасную игровую и образовательную деятельность; создание доступной и безопасной среды для оздоровления и социализации воспитанников
Обновить

## Overview
Humanitarian project application
The project title | Rainbow Courtyard
The Project duration, years | 1
Applicant organisation proposing the project
Organisation name | State Institution “Vasilishki Children’s Social Boarding School ‘Vasilki’”
Address | Grodno Region, Shchuchin District, Golovichpole Village, Yubileynaya Street, 2
Position of the contact person | Educator
Name, surname of the contact person | Svetlana Nikolaevna Petukhovskaya
Contact details for liaison | 375336552576
The Target group | Children with disabilities and special psychophysical development needs
Place of project realisation | Grodno Region, Shchuchin District, Golovichpole Village, Yubileynaya Street, 2
Justification of the problem taking into account the baseline situation in the project region | The region lacks a specialized, safe, and adapted playground for children with psychophysical disabilities; the lack of such facilities reduces opportunities for children to improve their health and develop their physical, cognitive, and creative skills.
Project Aim | Creating a safe and accessible environment for the physical, mental, and emotional development of children with disabilities and special psychophysical needs.
Project Summary | The project involves setting up a summer health camp where various activities will be held aimed at improving the health and developing the interests and abilities of children with disabilities who have special psychophysical development needs. As part of the project, children will participate in sports activities, creative classes, and other entertaining and educational activities. Particular attention will be paid to developing children's skills in healthy lifestyles, self-care, and behavioral culture.
Total project funding
Planned number of trenches | 1
Currency | BYN
Total | 25000
Donor funds | 25000
Co-financing | 0
Further activities at the end of the project | After completion of the project, the site will be used as a permanent resource for health and developmental activities for children at the boarding school during the summer. There are plans to hold regular sports, creative, and developmental events, as well as to involve new pupils. The experience gained in organizing and operating the site will be used to plan similar projects and disseminate methods of working with children with developmental disabilities in other institutions in the region.

## Project Objectives
The envisaged objectives during the project work:
Create conditions for a safe and accessible play environment adapted to the needs of children with disabilities and special psychological and physical development needs
develop creative potential and strengthen physical, mental, and emotional health
provide opportunities for active recreation and physical activity in the fresh air
organize diverse and interesting play activities that promote the development of various skills and abilities
create a favorable atmosphere for the development of friendly relationships between children
promote the development of self-care, independence, and responsibility skills in children

## Project Activities
Description of project activities:
Sports activities: relay races, outdoor games, adapted exercises
creative workshops: drawing, modeling, crafts, music lessons
developmental games and activities for cognitive and communication skills
teaching healthy lifestyle skills: hygiene, proper nutrition, behavioral culture
excursions and walks on the playground using adapted elements
play activities on safe, adapted slides, swings, carousels, and sandboxes

## Expected Result
Expected Result:
Increasing physical activity and improving the health of children with special psychophysical development needs
developing creative, cognitive, and communication skills
forming healthy lifestyle habits and behavioral culture
engaging children in useful and safe play and educational activities
creating an accessible and safe environment for the health and socialization of pupils

## Data aggregation
Humanitarian project application
Organisation name | State Institution “Vasilishki Children’s Social Boarding School ‘Vasilki’”
Address | Grodno Region, Shchuchin District, Golovichpole Village, Yubileynaya Street, 2
Position of the contact person | Educator
Name, surname of the contact person | Svetlana Nikolaevna Petukhovskaya
Contact details for liaison | 375336552576
The project title | Rainbow Courtyard
The Project duration, years | 1
The Target group | Children with disabilities and special psychophysical development needs
Place of project realisation | Grodno Region, Shchuchin District, Golovichpole Village, Yubileynaya Street, 2
Justification of the problem taking into account the baseline situation in the project region | The region lacks a specialized, safe, and adapted playground for children with psychophysical disabilities; the lack of such facilities reduces opportunities for children to improve their health and develop their physical, cognitive, and creative skills.
Project Aim | Creating a safe and accessible environment for the physical, mental, and emotional development of children with disabilities and special psychophysical needs.
Project Summary | The project involves setting up a summer health camp where various activities will be held aimed at improving the health and developing the interests and abilities of children with disabilities who have special psychophysical development needs. As part of the project, children will participate in sports activities, creative classes, and other entertaining and educational activities. Particular attention will be paid to developing children's skills in healthy lifestyles, self-care, and behavioral culture.
Planned number of trenches | 1
Currency | BYN
Total | 25000
Donor funds | 25000
Co-financing | 0
Further activities at the end of the project | After completion of the project, the site will be used as a permanent resource for health and developmental activities for children at the boarding school during the summer. There are plans to hold regular sports, creative, and developmental events, as well as to involve new pupils. The experience gained in organizing and operating the site will be used to plan similar projects and disseminate methods of working with children with developmental disabilities in other institutions in the region.
The envisaged objectives during the project work | Create conditions for a safe and accessible play environment adapted to the needs of children with disabilities and special psychological and physical development needs; develop creative potential and strengthen physical, mental, and emotional health; provide opportunities for active recreation and physical activity in the fresh air; organize diverse and interesting play activities that promote the development of various skills and abilities; create a favorable atmosphere for the development of friendly relationships between children; promote the development of self-care, independence, and responsibility skills in children
Description of project activities | Sports activities: relay races, outdoor games, adapted exercises; creative workshops: drawing, modeling, crafts, music lessons; developmental games and activities for cognitive and communication skills; teaching healthy lifestyle skills: hygiene, proper nutrition, behavioral culture; excursions and walks on the playground using adapted elements; play activities on safe, adapted slides, swings, carousels, and sandboxes
Expected Result | Increasing physical activity and improving the health of children with special psychophysical development needs; developing creative, cognitive, and communication skills; forming healthy lifestyle habits and behavioral culture; engaging children in useful and safe play and educational activities; creating an accessible and safe environment for the health and socialization of pupils
Обновить

## Справочник
Справочник валют
USD | Доллар США
EUR | Евро
GBP | Фунт стерлингов
CHF | Швейцарский франк
CNY | Китайский юань
BYN | Белорусский рубль
RUB | Российский рубль