## Общие сведения
Гуманитарная заявка
Наименование госоргана (организации)
УНП госоргана (организации)
Название проекта | «Народный фольклор и сказки России и Беларуси для детей-инвалидов «Сказки на двоих»
Продолжительность проекта, лет | 1
Организация-заявитель, предлагающая проект
УНП | 500031788
Название | Государственное учреждение «Василишковский детский социальный пансионат «Васильки»
Адрес | Гродненская обл .Щучинский р-н аг.Головичполье ул.Юбилейная, 2
Должность ответственного лица | Воспитатель
ФИО ответственного лица | Полуян Анна Зеноновна
Контактные данные для связи | 375336552576
Целевая группа | воспитанники ГУ «Василишковский детский социальный пансионат «Васильки», дети- инвалиды из России и Беларуси
Место реализации проекта | Гродненская обл .Щучинский р-н аг.Головичполье ул.Юбилейная, 2
Обоснование проблемы с учетом исходной ситуации в регионе реализации проекта | Несмотря на развитие инклюзивного образования, детям с инвалидностью доступ к устному народному творчеству, которое содержит в себе важные воспитательные, моральные и культурные коды, ограничен из-за отсутствия адаптированных материалов и инклюзивной среды. Наш проект позволит восполнить этот дефицит через аудиокниги, театрализации, творческие мастер-классы с участием самих детей. Проект направлен на создание инклюзивной культурно-образовательной среды для детей-инвалидов из России и Беларуси. Через адаптированные сказки, спектакли и мультимедийные форматы дети смогут прикоснуться к общему культурному наследию, укрепить чувство принадлежности к единому культурному пространству. Данный проект станет важным шагом в создании инклюзивного пространства для детей- инвалидов и будет способствовать более широкому распространению культуры и традиций.
Цель проекта | Создание доступного инклюзивного культурного пространства, способствующего культурной интеграции и развитию творческого потенциала, в котором дети с инвалидностью из России и Беларуси смогут познакомиться с богатством славянского фольклора.
Краткое содержание (суть) проекта | Создание инклюзивной культурно-образовательной программы для детей с тяжёлыми и множественными нарушениями развития через погружение в фольклор. Создание доступной и увлекательной среды для детей-инвалидов, способствуя их участию в культуре через изучение и сбор фольклора России и Беларуси, усиление культурных связей между Россией и Беларусью.
Финансирование проекта
Количество поступлений (план) | 1
Валюта | USD
Общая стоимость проекта | 28260
Средства донора | 28260
Софинансирование | 0
Дальнейшая деятельность по окончании проекта | Проведение инклюзивных спектаклей и фольклорных конкурсов, совместных интерактивных встреч, онлайн и офлайн мероприятий; организация интерактивных выставок детских рисунков и поделок по мотивам сказок; проведение пилотного тестирования с участием детей-инвалидов для доработки функционала и обучение педагогов и специалистов; поддержка и продвижение проекта через рекламные кампании в соцсетях, школах и общественных организациях, участие в образовательных мероприятиях и конференциях для привлечения внимания к проекту.

## Задачи проекта
Задачи, планируемые к выполнению в рамках реализации проекта:
Инклюзивность: создать инклюзивную среду и обеспечить доступность для детей с различными формами инвалидности
Интерактивность: разработать и создать инклюзивные форматы: аудиосказки, книги с крупным шрифтом, тактильные книги, мультимедийные материалы с переводом на язык жестов, что сделает изучение более увлекательным и доступным
Разработка интерактивной платформы: для расширения аудитории и обеспечения доступа к материалам проекта планируется создание веб-сайта с доступными историями, аудиозаписями и видеоматериалами
Создание инклюзивного сообщества: продумать, как сделать проект долгосрочным и устойчивым, наладить сотрудничество с другими учреждениями, организация творческих мастер-классов, где дети смогут не только услышать истории, но и попробовать сами рассказывать, сочинять, придумывать персонажей
Образовательный аспект: разработать контент, который поможет расширить представление о фольклоре России и Беларуси, исследование фольклорной традиции: команда проекта собирает материалы русского и беларуского фольклора: сказки, легенды, адаптируя их для детей-инвалидов
Подготовка сборника: работа над созданием сборника русских и беларуских сказок, адаптированных для детей с учётом их особенностей (в сборнике будут использоваться крупный шрифт, иллюстрации и аудиоформат
Поддержать межкультурный диалог между народами России и Беларуси
Развлекательный элемент: включить игровые и творческие элементы, которые будут удерживать внимание детей и способствовать их активному вовлечению
Разработать план возможности интеграции проекта в образовательные программы

## Мероприятия
Краткое описание мероприятий в рамках проекта:
Сбор и адаптация фольклора, подготовка платформы, формирование экспертной группы
Разработка образовательных материалов (текстовых, аудио и видео), проектно-сметной документации для создания платформы
Создание мультимедийной онлайн-платформы: разработка веб-сайта или мобильного приложения с поддержкой VR и AR, доступных для детей
Запуск онлайн-библиотеки (аудио, жестовый перевод), онлайн-занятия и мастер-классы по народным ремёслам и фольклору
Сенсорные и арт-терапевтические занятия

## Ожидаемые результаты
Ожидаемые результаты:
10 сказок в аудио, видео и печатной форме
Платформа с доступом для детей-инвалидов
Мероприятия в 5+ регионах

## Агрегация данных
Заявка на гуманитарный проект
Организация-заявитель, предлагающая проект | Государственное учреждение «Василишковский детский социальный пансионат «Васильки»
УНП | 500031788
Адрес | Гродненская обл .Щучинский р-н аг.Головичполье ул.Юбилейная, 2
Должность ответственного лица | Воспитатель
ФИО ответственного лица | Полуян Анна Зеноновна
Контактные данные для связи | 375336552576
Название проекта | «Народный фольклор и сказки России и Беларуси для детей-инвалидов «Сказки на двоих»
Продолжительность проекта, лет | 1
Целевая группа | воспитанники ГУ «Василишковский детский социальный пансионат «Васильки», дети- инвалиды из России и Беларуси
Место реализации проекта | Гродненская обл .Щучинский р-н аг.Головичполье ул.Юбилейная, 2
Обоснование проблемы с учетом исходной ситуации в регионе реализации проекта | Несмотря на развитие инклюзивного образования, детям с инвалидностью доступ к устному народному творчеству, которое содержит в себе важные воспитательные, моральные и культурные коды, ограничен из-за отсутствия адаптированных материалов и инклюзивной среды. Наш проект позволит восполнить этот дефицит через аудиокниги, театрализации, творческие мастер-классы с участием самих детей. Проект направлен на создание инклюзивной культурно-образовательной среды для детей-инвалидов из России и Беларуси. Через адаптированные сказки, спектакли и мультимедийные форматы дети смогут прикоснуться к общему культурному наследию, укрепить чувство принадлежности к единому культурному пространству. Данный проект станет важным шагом в создании инклюзивного пространства для детей- инвалидов и будет способствовать более широкому распространению культуры и традиций.
Цель проекта | Создание доступного инклюзивного культурного пространства, способствующего культурной интеграции и развитию творческого потенциала, в котором дети с инвалидностью из России и Беларуси смогут познакомиться с богатством славянского фольклора.
Краткое содержание (суть) проекта | Создание инклюзивной культурно-образовательной программы для детей с тяжёлыми и множественными нарушениями развития через погружение в фольклор. Создание доступной и увлекательной среды для детей-инвалидов, способствуя их участию в культуре через изучение и сбор фольклора России и Беларуси, усиление культурных связей между Россией и Беларусью.
Количество поступлений (план) | 1
Валюта | USD
Общая стоимость проекта | 28260
Средства донора | 28260
Софинансирование | 0
Дальнейшая деятельность по окончании проекта | Проведение инклюзивных спектаклей и фольклорных конкурсов, совместных интерактивных встреч, онлайн и офлайн мероприятий; организация интерактивных выставок детских рисунков и поделок по мотивам сказок; проведение пилотного тестирования с участием детей-инвалидов для доработки функционала и обучение педагогов и специалистов; поддержка и продвижение проекта через рекламные кампании в соцсетях, школах и общественных организациях, участие в образовательных мероприятиях и конференциях для привлечения внимания к проекту.
Задачи, планируемые к выполнению в рамках реализации проекта | Инклюзивность: создать инклюзивную среду и обеспечить доступность для детей с различными формами инвалидности; Интерактивность: разработать и создать инклюзивные форматы: аудиосказки, книги с крупным шрифтом, тактильные книги, мультимедийные материалы с переводом на язык жестов, что сделает изучение более увлекательным и доступным; Разработка интерактивной платформы: для расширения аудитории и обеспечения доступа к материалам проекта планируется создание веб-сайта с доступными историями, аудиозаписями и видеоматериалами; Создание инклюзивного сообщества: продумать, как сделать проект долгосрочным и устойчивым, наладить сотрудничество с другими учреждениями, организация творческих мастер-классов, где дети смогут не только услышать истории, но и попробовать сами рассказывать, сочинять, придумывать персонажей; Образовательный аспект: разработать контент, который поможет расширить представление о фольклоре России и Беларуси, исследование фольклорной традиции: команда проекта собирает материалы русского и беларуского фольклора: сказки, легенды, адаптируя их для детей-инвалидов; Подготовка сборника: работа над созданием сборника русских и беларуских сказок, адаптированных для детей с учётом их особенностей (в сборнике будут использоваться крупный шрифт, иллюстрации и аудиоформат; Поддержать межкультурный диалог между народами России и Беларуси; Развлекательный элемент: включить игровые и творческие элементы, которые будут удерживать внимание детей и способствовать их активному вовлечению; Разработать план возможности интеграции проекта в образовательные программы
Краткое описание мероприятий в рамках проекта | Сбор и адаптация фольклора, подготовка платформы, формирование экспертной группы; Разработка образовательных материалов (текстовых, аудио и видео), проектно-сметной документации для создания платформы; Создание мультимедийной онлайн-платформы: разработка веб-сайта или мобильного приложения с поддержкой VR и AR, доступных для детей; Запуск онлайн-библиотеки (аудио, жестовый перевод), онлайн-занятия и мастер-классы по народным ремёслам и фольклору; Сенсорные и арт-терапевтические занятия
Ожидаемые результаты | 10 сказок в аудио, видео и печатной форме; Платформа с доступом для детей-инвалидов; Мероприятия в 5+ регионах
Обновить

## Overview
Humanitarian project application
The project title | Folklore and fairy tales of Russia and Belarus for children with disabilities “Fairy tales for two”
The Project duration, years | 1
Applicant organisation proposing the project
Organisation name | State Institution “Vasilishki Children’s Social Boarding School ‘Vasilki’”
Address | Grodno Region, Shchuchin District, Golovichpole Village, Yubileynaya Street, 2
Position of the contact person | Educator
Name, surname of the contact person | Poluyan Anna Zenonovna
Contact details for liaison | 375336552576
The Target group | Students of the Vasilishkovsky Children's Social Boarding School “Vasilki”, disabled children from Russia and Belarus
Place of project realisation | Grodno Region, Shchuchin District, Golovichpole Village, Yubileynaya Street, 2
Justification of the problem taking into account the baseline situation in the project region | Despite the development of inclusive education, children with disabilities have limited access to oral folk art, which contains important educational, moral, and cultural codes, due to the lack of adapted materials and an inclusive environment. Our project will fill this gap through audiobooks, theatrical performances, and creative workshops involving the children themselves. The project aims to create an inclusive cultural and educational environment for children with disabilities from Russia and Belarus. Through adapted fairy tales, performances, and multimedia formats, children will be able to touch upon their common cultural heritage and strengthen their sense of belonging to a single cultural space. This project will be an important step in creating an inclusive space for children with disabilities and will contribute to the wider dissemination of culture and traditions.
Project Aim | Creating an accessible, inclusive cultural space that promotes cultural integration and creative development, where children with disabilities from Russia and Belarus can learn about the richness of Slavic folklore.
Project Summary | Creating an inclusive cultural and educational program for children with severe and multiple developmental disabilities through immersion in folklore. Creating an accessible and engaging environment for children with disabilities, promoting their participation in culture through the study and collection of Russian and Belarusian folklore, and strengthening cultural ties between Russia and Belarus.
Total project funding
Planned number of trenches | 1
Currency | USD
Total | 28620
Donor funds | 28620
Co-financing | 0
Further activities at the end of the project | Holding inclusive performances and folklore competitions, joint interactive meetings, online and offline events; organizing interactive exhibitions of children's drawings and crafts based on fairy tales; conducting pilot testing with the participation of children with disabilities to refine functionality and train teachers and specialists; supporting and promoting the project through advertising campaigns on social media, in schools, and public organizations, participating in educational events and conferences to draw attention to the project.

## Project Objectives
The envisaged objectives during the project work:
Inclusivity: create an inclusive environment and ensure accessibility for children with various disabilities
Interactivity: develop and create inclusive formats: audio stories, large-print books, tactile books, multimedia materials with sign language translation, which will make learning more engaging and accessible
Development of an interactive platform: to expand the audience and ensure access to project materials, we plan to create a website with accessible stories, audio recordings, and video materials
Creation of an inclusive community: to consider how to make the project long-term and sustainable, to establish cooperation with other institutions, to organize creative workshops where children can not only hear stories, but also try to tell them themselves, compose, and invent characters
Educational aspect: develop content that will help broaden the understanding of Russian and Belarusian folklore, research folklore traditions: the project team collects materials on Russian and Belarusian folklore, such as fairy tales and legends, and adapts them for children with disabilities
Preparation of a collection: work on the creation of a collection of Russian and Belarusian fairy tales adapted for children, taking into account their specific needs (the collection will use large print, illustrations, and audio format)
Develop a plan for the integration of the project into educational programs
Support intercultural dialogue between the peoples of Russia and Belarus
Entertainment element: include games and creative elements that will hold children's attention and encourage their active involvement

## Project Activities
Description of project activities:
Collecting and adapting folklore, preparing the platform, forming an expert group
Developing educational materials (text, audio, and video), design and estimate documentation for creating the platform
Creation of a multimedia online platform: development of a website or mobile application with VR and AR support, accessible to children
Launch of an online library (audio, sign language translation), online classes and master classes on folk crafts and folklore
Sensory and art therapy classes

## Expected Result
Expected Result:
10 fairy tales in audio, video, and print formats
Platform accessible to children with disabilities
Events in 5+ regions

## Data aggregation
Humanitarian project application
Organisation name | State Institution “Vasilishki Children’s Social Boarding School ‘Vasilki’”
Address | Grodno Region, Shchuchin District, Golovichpole Village, Yubileynaya Street, 2
Position of the contact person | Educator
Name, surname of the contact person | Poluyan Anna Zenonovna
Contact details for liaison | 375336552576
The project title | Folklore and fairy tales of Russia and Belarus for children with disabilities “Fairy tales for two”
The Project duration, years | 1
The Target group | Students of the Vasilishkovsky Children's Social Boarding School “Vasilki”, disabled children from Russia and Belarus
Place of project realisation | Grodno Region, Shchuchin District, Golovichpole Village, Yubileynaya Street, 2
Justification of the problem taking into account the baseline situation in the project region | Despite the development of inclusive education, children with disabilities have limited access to oral folk art, which contains important educational, moral, and cultural codes, due to the lack of adapted materials and an inclusive environment. Our project will fill this gap through audiobooks, theatrical performances, and creative workshops involving the children themselves. The project aims to create an inclusive cultural and educational environment for children with disabilities from Russia and Belarus. Through adapted fairy tales, performances, and multimedia formats, children will be able to touch upon their common cultural heritage and strengthen their sense of belonging to a single cultural space. This project will be an important step in creating an inclusive space for children with disabilities and will contribute to the wider dissemination of culture and traditions.
Project Aim | Creating an accessible, inclusive cultural space that promotes cultural integration and creative development, where children with disabilities from Russia and Belarus can learn about the richness of Slavic folklore.
Project Summary | Creating an inclusive cultural and educational program for children with severe and multiple developmental disabilities through immersion in folklore. Creating an accessible and engaging environment for children with disabilities, promoting their participation in culture through the study and collection of Russian and Belarusian folklore, and strengthening cultural ties between Russia and Belarus.
Planned number of trenches | 1
Currency | USD
Total | 28620
Donor funds | 28620
Co-financing | 0
Further activities at the end of the project | Holding inclusive performances and folklore competitions, joint interactive meetings, online and offline events; organizing interactive exhibitions of children's drawings and crafts based on fairy tales; conducting pilot testing with the participation of children with disabilities to refine functionality and train teachers and specialists; supporting and promoting the project through advertising campaigns on social media, in schools, and public organizations, participating in educational events and conferences to draw attention to the project.
The envisaged objectives during the project work | Inclusivity: create an inclusive environment and ensure accessibility for children with various disabilities; Interactivity: develop and create inclusive formats: audio stories, large-print books, tactile books, multimedia materials with sign language translation, which will make learning more engaging and accessible; Development of an interactive platform: to expand the audience and ensure access to project materials, we plan to create a website with accessible stories, audio recordings, and video materials; Creation of an inclusive community: to consider how to make the project long-term and sustainable, to establish cooperation with other institutions, to organize creative workshops where children can not only hear stories, but also try to tell them themselves, compose, and invent characters; Educational aspect: develop content that will help broaden the understanding of Russian and Belarusian folklore, research folklore traditions: the project team collects materials on Russian and Belarusian folklore, such as fairy tales and legends, and adapts them for children with disabilities; Preparation of a collection: work on the creation of a collection of Russian and Belarusian fairy tales adapted for children, taking into account their specific needs (the collection will use large print, illustrations, and audio format); Develop a plan for the integration of the project into educational programs; Support intercultural dialogue between the peoples of Russia and Belarus; Entertainment element: include games and creative elements that will hold children's attention and encourage their active involvement
Description of project activities | Collecting and adapting folklore, preparing the platform, forming an expert group; Developing educational materials (text, audio, and video), design and estimate documentation for creating the platform; Creation of a multimedia online platform: development of a website or mobile application with VR and AR support, accessible to children; Launch of an online library (audio, sign language translation), online classes and master classes on folk crafts and folklore; Sensory and art therapy classes
Expected Result | 10 fairy tales in audio, video, and print formats; Platform accessible to children with disabilities; Events in 5+ regions
Обновить

## Справочник
Справочник валют
USD | Доллар США
EUR | Евро
GBP | Фунт стерлингов
CHF | Швейцарский франк
CNY | Китайский юань
BYN | Белорусский рубль
RUB | Российский рубль